## 1601-CS Office
Strategy Objective | Code | Program | Activity | Budget | Output/Service Target | Target | Action | Due Date | Comments/Risks | Progress
| 1.1 | Statistical Legislation Governance | MFBA |  | Oversee the statistical governance through the Statistics Advisory Council mandated to support the Chief Statistician with oversight of VBoS operations and approval of Policys, long term plans. In addition, the endorsement of 2025 Annual Report and 2026 Business Plans. | x2 SAC Meeting held |  | Dec
[6 empty] | x2 Regulations endorsed by SAC |  | Sept
[6 empty] | NSDS implementation report endorsed by SAC |  | Dec
| 1.2 | Management & Administration of the Vanuatu Bureau of Statistics | MFBA |  | Oversee the daily administration of the department through efficient, effective Management of the programs and activities as outlined in the VBoS 2026 Business Plan | Quarterly report provided to DGs Office on Business Plan progress. |  | Dec
| 1.3 | Budgeting & Financial Management | MFBA |  | Oversee the preparation and Management of annual budget for the department and ensure it reflects the Business Plan priorities | Quarterly report provided DGs Office on Budget Mgt. |  | Dec
To exercise control over the expenditure of all funds made available to the Department as per PFEM Act and also management of the department assets.
[5 empty] | Coordinate the development of annual budget and facilitated the submission to the Ministerial Budget committee (MBC). | VBoS 2027 Budget and NPP submitted |  | June
| 1.4 | Human Resource Management and Development | MFBA |  | Ensure performance review of staff are conducted. | Staff Appraisal for 2025 submitted and 2026 Beginning and Mid Year subbmited |  | Feb
[5 empty] | Take leading role to oversee the Individual Annual Work Plan. |  |  | Dec
[5 empty] | Manage staff to undergo short- and long-term training based on the department needs whenever required. | Skills Gap Analysis conducted |  | June
[5 empty] | Ensure department staff annual leave are manageable. | Annual leave balance of individual staff is up to-date (Must not exceed at 21 days in total) |  | Dec
[5 empty] | Management of staff Retirement | Retirement budget is included in the Department Annual budget. |  | June
| 1.5 | Planning and Policy | MFBA |  | To effectively supervise the development, revision and Implementation of major policies for the efficient operation and management of the department. | Review on the provision of relevant policy. |  | Sept
[5 empty] | Ensure that the departments Business Plan accommodates relevant sector objectives under the National Sustainable Development Plan (NSDP) and sector Plans | 2027 Annual Business Plan completed by December 2026. |  | Dec
[5 empty] | Provide accurate policy advice to DG, Minister and department officials/or stakeholders | A timely advice to Minister and DG MFEM is required. |  | Ongoing
[5 empty] | Participate and Contribute constructively to the development of MFEM Corporate Plan aligning with relevant Pillars and policy objectives under NSDP. | MFEM Corporate Plan related VBoS targets and activities updated in Annual Report of VBoS |  | Dec
[5 empty] | Develop a communication policy, regulation and strategy to promote the use of data and the services provided by the statistical office in line with the Statistics Act. | VBoS Communications Regulation Order signed |  | July
| 1.6 | Project Management (Censes &Survey) | MFBA |  | Oversea the design, budget acquisition, program / activities implementation and reporting. Report provided on the completion of projects and dateline met submitted to the Donor Partners. | Labour Force Survey - Report Launched in March |  | Dec
Household Income & Expenditure Survey - Data collection
NCD STEPS Survey - Design and Implementation
| 1.7 | Public Relations & Stakeholder Engagement | MFBA |  | Co-ordinate the departments programs and activities that involve other government Ministries, Private Sectors, International Organization on Important Issues that requires collaborative efforts. | x5 Partnership Agreements signed (MOU, MOA, Grant Agreement, etc..) |  | Dec
[6 empty] | Report on stakeholder engagement to be reflected in Annual Report |  | Dec
| 1.8 | Reporting | MFBA |  | Ensure that Department provide Annual Report annually on the progress of Business Plan Implementation | 2025 Annual Report Submitted to DGs Office |  | Feb
[6 empty] | 1st Draft of Annual Report submitted to DG’s office by 31st of December 2026 |  | Dec
|  | TOTAL BUDGET |  | 0

## 1602-DCM
Strategy Objective | Code | Program | Activity | Budget | Output/Service Target | Target | Action | Due Date | Comments/Risks | Progress
| 2.1 | 10 year Data Collection Plan | MFDA | Donor | Labour Force Survey
DEVELOP A HARMONIZED NATIONAL STATISTICS OFFICE |  |  |  |  | 2.1.1. Administration Report | 1 | 2024-2025 Labour Force Survey | 2026 |  | In progress
|  |  |  | Donor | HIES
[5 empty] | 2.1.2.. Training of Trainers | 1 | 2025 HIES | 2026-2027 | 1. Natural Disaster (Cyclone Season) | Complete
[5 empty] | 2.1.3. Training of Enumerator | 1 | Assist Port Vila |  | 2. Enumerator Turnover | Complete
[5 empty] | 2.1.4.. Fieldwork Monitoring of Enumerators | 1 | Assist Port Vila |  | 3. Delay of Funds | In progress
|  |  |  | Donor | NCD SURVEY
[5 empty] | 2.1.5. Provide Technical Support | 1 | Field work collection monitoring in Sanma | 2026 |  | In progress
| 2.2 | Production of Regular Pulbications | MFDA | 500000 | CPI
[5 empty] | 2.2.1. 26 Data Collection & 26 Entries | 26 | CPI Forhtnighly Data Collection |  | 1. Delay in prining | In progress
[5 empty] | 2.2.2. 4 Data Collection | 4 | CPI Quaterly Data Collection | 2026-12-31 | 2. No available vehicle | In progress
3. Unforseen circumstances
MARKET SURVEY
[5 empty] | 2.2.3. 26 Data Collection & 26 Entries | 26 | Market Survey Fornightly Data Collection & Entry | 2026-12-31 |  | In progress
|  |  |  | 100000 | PROVINCIAL REPORTS
[5 empty] | 2.3.4. Provincial Statistical Indicator- (PSI) | 6 |  | 2026-12-31 |  | In progress
| 2.3 | DCM Reporting and Development | MFDA |  | STAFF WORKPLAN
[5 empty] | 2.3.1. Annual long-term goals with monthly reviews | 12 | DCM Staff Monthly Reporting | 2026-12-31 |  | In progress
|  |  |  | 100000 | QUATERLY SECTION MEETINGS
[5 empty] | 2.3.2. DCM Quaterly Section Meetings | 4 |  | 2026-12-31 |  | In progress
|  |  |  | 200000 | CAPACITY BUILDING
[5 empty] | 2.3.3. Capacity Building for DCM Staffs through online, in-house and external trainings. (Survey Solutions, Tableau, R) | 4 |  | 2026-12-31 |  | Not yet Started
QUATERLY REPORTING TO CS OFFICE
[5 empty] | 2.3.4. Quaterly Report to Executive and CS Office | 4 |  | 2026-12-31 |  | In progress
| 2.4 | Standard Operating Procedure (SOP) | MFDA | 100000 | 2.4.1. PSI Final SOP Report | 1 |  | 2026-03-31 |  | In progress
[5 empty] | 2.4.2. CENSUS Final SOP Report | 1 |  | 2026-03-31 |  | In progress
[5 empty] | 2.4.3. SURVEY Final SOP Report | 1 |  | 2026-03-31 |  | In progress
[5 empty] | 2.4.4. CPI Final SOP Report | 1 |  | 2026-03-31 |  | In progress
[5 empty] | 2.4.5. MARKET SURVEY Final SOP Report | 1 |  | 2026-03-31 |  | In progress
| 2.5 | Other Activities | MFDA |  | 2.5.1.STAKEHOLDER SUPPORT RELATIONSHIP DEVELOPED | 1 |  | 2026-12-31 |  | In progress
|  |  |  | ADB | 2.5.2. Ad-hoc Survey - Provide Technical support for a smooth running process of the survey | 1 |  |  |  | Not yet Started
[5 empty] | 2.5.3. Pacific Mobility Survey Wave 2 - Provide Technical support for a smooth running process of the survey | 1 |  |  |  | In progress
|  | TOTAL BUDGET |  | 1000000

## 1603-Admin&Finance
Strategy Objective | Code | Program | Activity | Budget | Output/Service Target | Target | Action | Due Date | Comments/Risks | Progress
DEVELOP A HARMONIZED BUREAU OF STATISTICS | ADMINISTRATION
|  | Annual Planning | MFBB | 2000000 | BUSINESS PLAN
[5 empty] | 3.1.1. 2026 Business Plan Reviewed | 1 | Coordinate 2026 BP Review | 2026-04-30 | Office change of priorities and Commitments | Not Yet Started
[5 empty] | 3.1.2. 2027 Business Plan Workshop Conducted | 1 | Coordinate 2027 Business Plan Workshop Arrangements | 2026-04-30 | Mitigation: Review workplan to align with the changes | Not Yet Started
[5 empty] | 3.1.3. 2027 Business Plan Compiled and Signed | 1 | Compile 2027 BP and Submit to DSPPAC and NSAC for review and approval | 2026-11-30 |  | Not Yet Started
|  |  |  | 100000 | ANNUAL REPORT
[5 empty] | 3.1.4. 2025 Annual Report submit to NSAC | 1 | Develop 2025 Annual Report Template. Liaise with Executives for review | 2026-01-30 | Information required is lost | In Progress
| 3.1 | [5 empty] | Compile the Draft and submit to NSAC | 2026-02-27 | Mitigation: Address lost- of information in the AR and inform Ministry accordingly
[7 empty] | 2025 Annual Report signed and submit to MFEM Minister | 2026-03-30
EXECUTIVE AND STAFF MEETINGS
|  |  |  | 600000 | 3.1.5.Executive Meetings | 11 | Coordinate Executtive Meetings | Monthly | Meeting could not held due to Natural Disaster | Up to date
|  |  |  | 400000 | 3.1.6. Staff Meetings | 2 | Coordinate Staff Meetings | Quaterly | Mitigation: Resort to Video Conferencing | Not Yet Started
[5 empty] | ADMIN AND FINANCE SECTION MEETINGS |  |  |  | Meeting could not held due to Natural Disaster | Up to date
|  |  |  | 180000 | 3.1.7. Admin and Finance Quaterly Meetings | 4 | Coordinate Section Meeting | Quaerly | Mitigation: Resort to Video Conferencing
| 3.2 | Front Desk Management Report | MFBB | 2000000 | 3.2.1. Incoming and Outgoing Correspondence Report | 4 | Develop a record of Incoming and Outgoing correspondence | Quarterly | Services are not delivered due to natural disaster and pandemic | Up to date
[5 empty] | 3.2.2. Customs Services Complaints Report |  | Develop a record excel of Customer Complaints |  | Mitigation: Business Continuity Plan - Disaster SOP | Up to date
[5 empty] | 3.2.3. Official Function Logistics Report and Admin Expenses |  | Develop a record excel for Official Functions logistics |  |  | Up to date
| 3.3 | Filing Management System | MFBB |  | 3.3.1. A Filing System is developed for LPO | 1 | Hire an Intern to do filing for LPO Fund 2, LPO for Fund 4 and Incoming and outgoing correspondence in hard copies and upload to cloud for Admin and Finance to access | 2026-03-30 |  | Complete
[5 empty] | 3.3.2. A Filing System is developed for Incoming and Outgoing Correspondence | 1 |  | 2026-03-30 | Natural disaster destroy filing or filing lost | Complete
[5 empty] | 3.3.4. A Filing System is developed for Project LPOs | 1 |  | 2026-03-30 | Mitigation: Scan all files to share drive or one drive | Complete
[5 empty] | 3.3.5. Staff Profiling (Personal files updated) - FMIS | 52 |  | 2026-03-30 |  | In Progress
| 3.4 | Asset procurement & Registration | MFBB | 50000 | 3.4.1. Asset Reocrds Up to Date - Quaterly Reporting | 4 | Prepare Asset Procurement | Quarterly | Poor Management of assets allocated to staffs | Not Yet Started
[7 empty] | Prepare Asset Form |  | Assets lost and damage
[5 empty] | 3.4.2. Asset Registry System Implemented (SLC Assistance) | 1 | Update the Asset Registry | 2026-04-30 | Miigation: Quarterly follow up on the status of Asset and dispose assets with worn conditions | In Progress (Access On and Off)
Liaise with Finance for Asset Number
Asset disposal Updates
Develop an Asset Excel Record
| 3.5 | Fleet Management and Reporting | MFBB | 900000 | 3.5.1. VBoS Vehicle Log Book Updates | 1 | Update the vehicle Log Book | 2026-01-30 | Poor Vehicle Maintenance | Up to date - G221 Pending
[7 empty] | Liaise with a Printing Company to develop a vehicle log book for VBoS |  | Mitigation: Schedule vehicle maintenance and cross check fuel logs
[5 empty] | 3.5.2. Fuel Consunption and Vehicle Inspection Reporting | 4 | Prepare fuel consumption and vehicel | Quarterly |  | Up to date
[7 empty] | Inspecion Report |  | No funds available
[5 empty] | 3.5.3. New Vehicle for Admin and Finance | 1 | Liaise with CS and PSC for New Vehicle | 2026-03-30 | Mitigation: 2027 Proposal or Project Funds | Pending DG Approval
| 3.6 | Development of Policies and Guidelines | MFBB |  | 3.6.1. HEALTH AND SAFETY POLICY AND GUIDE | 1 | Develop a Health and Safety Policy and Guide Template | 2026-06-30 | Delay in development and implementation of the policy | Not Yet Started
[7 empty] | Compile with Disaster Risk SOP | 2026-06-30 | Mitigation: Review Business Plan deadline to align the workload to achieve the objective
[7 empty] | Present the Health and Safety with Team | 2026-04-30
[7 empty] | Launch the Health and Safety Policy and Guide | 2026-06-30
[5 empty] | 3.6.2. PROMEDIC MEMBERSHIP | 1 | Liaise with Pro Medic for VBoS Membership | 2026-06-30 | No funds available to cater for the Membership Fee | In Progress
Mitigation - Seek Support from other sources
[5 empty] | 3.6.3. ADMIN HR AND FINANCE SOPs | 1 | Review Admin, HR and Finance SOP | 2026-05-30 | SOP implemented but Not followed | Pending Consultation
[7 empty] | Disseminate the review version |  | Mitigation: Call Section Meeting to comply
| 3.7 | Administration Oversight | MFBB | 30000 | 3.7.1. RUBBISH RECYCLING | 1 | Develop a recycle process | 2026-01-15 | Recycling Initiative and process not adhere to | In Progress
[7 empty] | Liaise with Executives for Approval |  | Mitigation: Review the recycle process and call staff meeting to raise concern
Purchase the recycle bins
[7 empty] | Implement the Recycling Initiative | 2026-01-30
|  |  |  | 150000 | 3.7.2. MONTHLY CLEAN UP & HEALTH AWARENESS | 12 | Coordinate the Monthly Clean Up for VBoS Staffs | Monthly |  | Up to date
[5 empty] | 3.7.3. PREMISES SECUIRTY | 1 | Liaise with Secuirty Businesses for a Guard |  | No funding to hire a security guard | MFEM Provide Assistance
[5 empty] | 3.7.4. A Security Guard In Place | 1 | Develop a Contract with Supplier |  | Mitigation: MFEM to provide a Security
[7 empty] | Security Report for Duty | 2026-01-30
|  |  |  | 40000 | 3.7.5. QUARTERLY HEALTH CHECK UP FOR STAFFS | 4 | Liaise with VCH for Medical Checkups | Quarterly |  | In Progress
[5 empty] | 3.7.6 REVIEW VBOS SOCIAL CLUB |  | Develop a VBoS Social Club Constitution
[5 empty] | VBoS Social Club Constitution | 1 | Appoint Social Club Members | 2026-04-30 |  | In Progress
[5 empty] | VBoS Social Club Committee Appointment | 1 | Launch the New Social Club
HUMAN RESOURCE AND DEVELOPMENT
| 3.8 | Domestic and Overseas Mission | MFBB |  | 3.8.1. Domestic Missions Reporting | 4 | Facilitate the domestics mission logistics | 2026-12-31 | Issues with Flight Cancellation | Up to date
[7 empty] | Mission Report submitted to Admin |  | Mitigation: Resort to next available means of
[7 empty] | Action Plan Monitored |  | Transport
[5 empty] | 3.8.2. Overseas Mission Reporting | 4 | Facilitate overseas mission logistics | 2026-12-31 | Issue with Visa Application | Up to date
[7 empty] | Mission Report submitted to PSC |  | Mitigation: Liaise with MoFA for assistance
Action Plan Monitored
| 3.9 | Management Visit to Provinces | MFBB | 200000 | 3.9.1. Torba Management and Santo Management Visit | 2 | Plan and make arrangements | 2026-06-30 | Funding issues and committed priorites | Not Yet Started
[7 empty] | Submit Report to CS Office | 2026-08-30 | Mitigation: Seek funding assistance or video
|  |  |  | 200000 | 3.9.2. Malampa and Penama Management Visit |  | Follow up with Action |  | conferencing with Provincial Staffs
| 3.1 | Staff Training and Development | MFBB | Donor | 3.10.1. Training and Development Reporting | 2 | Identify Training Needs | Quaterly | Forms not approved in time | Up to date
[7 empty] | Identify Training Opportunities |  | Mitigation: Advise PSC before Officer travels
[7 empty] | Seek funding for Training and Logistics |  | Prepare approval a month before travel month
Coordinate Training
|  |  |  | Donor | ADMIN & FINANCE TRAINING OPPORTUNITES |  | Identify Training Opportunities |  | Funding Issues and committed priorites | In Progress
[5 empty] | 3.10.2. Record Keeping and Filing Management Training for Admin | 1 | Seek funding for Training and Logistics | 2026-12-31 | Mitigation: Find trainings offered on ground
[5 empty] | 3.10.3. Finance and Budget Training for Finance Officers | 1 | Officer Attend Training - Report Submit to Admin and Deputy
| 3.11 | Staff Leave Management | MFBB |  | 3.11.1. Leave Management Reporting | 12 | Monitor Work Attendance and ensure | Monthly | Staff do not complete leave forms | In Progress
[7 empty] | Officers adhere to office hours and provide concultation for officers who do not comply. |  | Mitigation: Manager to sign off on the leave form and attach it with time machine records for Admin to process to HRM
[5 empty] | 3.11.2. Leave Payout | 1 | If needed - seek approval for leave payout | 2026-12-31 | No funding for leave payout | Not Yet Started
Mitigation: Seek funding assistance
| 3.12 | Staff Grievacnes Management | MFBB |  | 3.12.1. All Staff Grievances are addressed in the financial year | 100% | Develop an excel of Staff Grievances | 2026-12-31 | Staff grievances not addressed | Up to date
[7 empty] | Review and Advice if needed |  | Mitigation: Seek advice from HRM and
[7 empty] | Facilitate request to HRM and PSC |  | PSC
| 3.13 | Resource Management | MFBB | 150000 | 3.13.1. ORGANIZATIONAL STRUCTURE
[5 empty] | Transpose Structure and Review JD Implemented | 1 | Liaise with PSC for the Transpose Structure and JDs | 2026-01-31 | Budget not allocated | Complete
[5 empty] | 2025 Restructure submit to PSC | 1 | Restructure Submit to PSC | 2026-03-31 | Mitigation: Supplementary | Pending Approval from PSC
3.12.2. RECRUITMENT
[5 empty] | All VBoS Positions fully occupied | 100% | Seek Direct Appoinments for Interns and staffs with satisfactory performance | 2026-06-30 | High Rate of Turnover | In Progress
Mitigation: Employ graduates on Intern basis
3.12.3. PERFORMANCE MANAGEMENT
[5 empty] | Appraisal - Section A Workplan submit to HRM | 52 | Section A workplans | 2026-01-30 | Delay in submission | Complete
[5 empty] | Appraisal - Section B Mid-year Review submit to HRM | 52 | Section B Mid-year review | 2026-06-30 | Mitigation: Submit File with received forms | Not Yet Started
[5 empty] | Appraisal - Section C End of Year Submit to HRM | 52 | Section C- End of Year | 2026-12-15 | Those not submited can be submitted later | Not Yet Started
FINANCIAL MANAGEMENT
| 3.14 | Annual Budget | MFBB | 80000 | 3.14.1. 2026 Budget Supplementary Window | 1 | Liaise with CS for Budget Supplementary and facilitate | 2026-02-27 | Office change of priorties and commitments | In Progress
[5 empty] | 3.14.2. 2027 Budget Workshop | 1 | Coordinate budget Workshop | 2026-05-30 | Mitigation: Review and make adjustment to budget spending | Not Yet Started
[5 empty] | 3.14.3. 2027 Budget Input to VBMS | 1 | Facilitate 2027 Budget Input VBMS | 2026-06-30 |  | Not Yet Started
| 3.15 | Financial Management and Monitoring | MFBB |  | 3.15.1. DESIGNATED SIGNATORIES
[5 empty] | 2026 Designated Signatories Form Complete | 1 | Liaise with CS for designated signatories and submit to Finance | 2026-01-30 | System Down | Complete
[5 empty] | 3.15.2. LPO COMMITMENTS AND RECONCILIATION |  |  |  | Mitigation: Manual Payment Form or Journal for Govt Depts | Up to date
[5 empty] | All LPO Commitments Reconciled | 100% | Commit LPO and approvals
[5 empty] | Manage all Low and High value Procurement |  | Provide Quarterly updates on oustanding | Quarterly
| 3.16 | Financial Reporting | MFBB |  | 3.16.1. MONTHLY FINANCIAL REPORTING | 12 | Prepare Expenditure and Budget | Monthly | System Down | Up to date
[5 empty] | Expenditure and Budget Monthly Updates in Excel Format |  | Excel Tablulate |  | Mitigation: Exract Report Weekly from system
Send to VBoS Execuives
[5 empty] | 3.16.2. QUARTERLY FINANCIAL REPORTING | 4 | Review all Fund 2 cost centers | Quaterly | System Down | In Progress
[5 empty] | Expenditure and Budget Summary Report |  | Reconcil all LPOs and provide a |  | Mitigation: Exract Report Weekly from system
Report to CS Office
| 3.17 | National project and in-house project support | MFDB |  | 3.17.1. HIES FINANCIAL MANAGEMENT
[5 empty] | Commitment Project LPO Payments | 100% | Review Invoice before comit LPO | On-going | Change of Program and Work Plans | Up to date
[5 empty] | HIES Project Expenditure and Budget Updates Excel Format | 12 | Extract payment info and prepare report | Monthly | Syste Down | Up to date
[7 empty] | to Project Coordinator and CS Office |  | Mitigation: Exract Report from System
[5 empty] | HIES Project Financial Reporting | 4 | Prepare report base on expenditure, budget, asset, challenges and way forwaard | Quarterly | Mitigation: Develop an excel record payment committed. | In Progress
| TOTAL BUDGET |  |  | 7080000

## 1605-SLC
Strategy Objective | Code | Program | Activity | Budget | Output/Service Target | Target | Action | Due Date | Comments/Risks | Progress
DEVELOP A HARMONIZED NATIONAL STATISTICS OFFICE | 5.1 | Publication, Dissemination & Information | MFDB | 30000 | 5.1.1. Maintain release calendar; enhance website tools; produce user guides & infographics | 1 | Maintain and publish an annual release calendar | Jan | Delays in receiving finalized datasets from sections
|  |  |  | 0 | 5.1.2. Disseminate Dec “25 through Nov 25’ Monthly Reports (Trades & Tourism) | 1 | Update VBOS website and upload monthly, quarterly, and annual reports | On-going | Limited IT capacity affecting website updates
|  |  |  | 0 | 5.1.3. Disseminate 4th qtr. 2025 and 1st, 2nd, & 3rd qtr. 2025 reports for QSI, CPI and MS | 1 | Produce infographics, video explainers, and user guides | April | Budget constraints for multimedia materials
|  |  |  | 0 | 5.1.4. Disseminate All Annual Reports (GDP highlights, etc..) | 1 | Conduct training sessions for ministries, media, and schools | April | Low participation in public training sessions
|  |  |  | 30000 | 5.1.5. Disseminate Ad hoc Reports (Agriculture Census Report, NPHC Monographs, Business Survey Reports, MICS Report, etc.) | 1
|  |  |  | 300000 | 5.1.6. Conduct training sessions for ministries, schools & media on stats use | 1
|  |  |  | 100000 | 5.1.7. Produce short video explainers/animated infographics for major releases | 1
| 5.2 | Methods & Standards Framework Development |  |  | 5.2.1. Development of the 5year Methods & Standards Strategy Plan | 1 | Develop the 5-year Methods & Standards Strategy Plan | June | Limited staff technical expertise to finalize manuals
[7 empty] | Finalize and publish the Data Standard Manual | June | Unpredictatble delayed in collaboration with Economics Section
[5 empty] | 5.2.2. Development of the Data Standard Manual | 1
[5 empty] | 5.2.3. Implementing the Generic Statistical Business Process Model (GSBPM) | 1 | Implement and document GSBPM visual process flows for CPI, GDP, and Trade | June | Lack of alignment across sections on standard definitions.
| 5.3 | Digital Data Collection & Processing |  |  | 5.3.1. Metadata Management: Share best practices on building and maintaining a central metadata repository for all surveys and censuses. | 1 | Document metadata for HIES and ad-hoc surveys | Dec | Incomplete or outdated metadata from survey teams
|  |  | MFDB |  |  |  | Regularly update the NSDP Indicator Platform | On-going | Technical downtime of the indicator platform - data fragmentation
|  |  |  | 20000 | 5.3.2. Regular update of the NSDP Indicators Platform | 1 | Coordinate with survey teams to maintain metadata completeness | Dec | Limited staff capacity to maintain continuous updates
| 5.4 | Data Access & Dissemination Standards |  | 150000 | 5.4.1. Support VBOS in improving its statistical website for easy data access, dashboards, and API integration. | 1 | Support VBOS website redesign with dashboards and APIs | June | Security risks relating to microdata access
|  |  | MFDB |  | 5.4.2. Guidance on managing microdata access, data anonymization, and licensing policies to protect privacy while improving accessibility. | 1 | Develop guidelines on microdata access and anonymization | June | Inadequate anonymization practices leading to privacy concerns
|  |  |  | 150000 | 5.4.3. Training on modern data visualization, infographics, and public communication standards. | 1 | Train staff on data visualization, infographics, and communication | March | Slow website modernization due to limited technical resources
| 5.5 | Data Quality Assurance & Evaluation | MFDB |  | 5.5.1. Develop the assurance checklists for the most critical outputs (e.g., CPI, GDP, Trade statistics) | 1 | Develop quality assurance checklists for CPI, GDP, and Trade statistics | June | Inconsistent application of QA procedures across sections
[7 empty] | Test and validate QA tools with responsible sections | Jan-Dec | Staff unfamiliarity with new QA requirements
[7 empty] | Integrate QA steps into regular production cycles | Jan-Dec | Delays in validation due to limited technical reviewers
| 5.6 | Innovation & System Modernization |  | 10000 | 5.6.1. Develop real-time dashboards to track enumerator progress, completion rates, and data quality flags. | 1 | Develop real-time dashboards for survey progress and data quality | Jan | Cybersecurity vulnerabilities if systems are not properly maintained
|  |  |  | 160000 | 5.6.2. Introduce secure cloud-based systems for storing and backing up raw and processed data. | 1 | Implement cloud-based storage solutions and secure access protocols | June | Integration issues between new and existing systems
|  |  | MFDB |  | 5.6.3. Implement secure logins, encryption, and data access protocols for sensitive datasets. | 1 | Roll out encryption, secure logins, and data governance framework. | Dec | Limited staff capacity to manage modern systems
[5 empty] | 5.6.4. Integrate Power BI, Tableau, or R Shiny for interactive data visualization and real-time dashboards. | 1 | Develop AI chatbot and mobile-friendly VBOS website | Dec
[5 empty] | 5.6.5. Develop basic AI chatbot to answer FAQs about census, surveys, or key indicators. | 1 | Implement 3CX phone system for centralized call management | Feb
[5 empty] | 5.6.6. Develop mobile friendly portal for key reports and indicators | 1
[5 empty] | 5.6.7. Development of the Vanuatu Data Protal | 1
[5 empty] | 5.6.8. Introduction of 3cx phone system | 1
| 5.7 | Technical Assistance & Capacity Building |  |  | 5.7.1. Statistical Methods Training: Workshops on survey sampling, weighting, variance estimation, seasonal adjustment, data anonymization and modern estimation techniques. | 1 | Deliver workshops on sampling, estimation, anonymization, and classification standards | March | Training fatigue or low attendance from NSS stakeholders
|  |  | MFDB |  | 5.7.2. Standards & Classifications / Quality Framework training | 1 | Conduct Power BI training and practical sessions | March | Limited financial resources for repeated training
[7 empty] | Complete the comprehensive review of NSDP indicators and trends | April | Staff turnover reducing institutional knowledge
|  |  |  | 1000000 | 5.7.3 Provide training on Microsoft Power BI | 1 | Provide ongoing support for CAPI, survey processing, data cleaning, and dashboard monitoring | Ongoing
[5 empty] | 5.7.4. Review of the National Sustainable Plan (NSDP) | 1
| 5.8 | Survey Training & Capacity Support |  |  | 5.8.1. Technical support to survey CAPI hosting" (Questionnaire design and uploading to the server, managing the questionnaire on the server, and assigning usernames to fieldworkers and supervisors) | 1 | Support questionnaire design, server upload, and CAPI user management | Ongoing | Tablet or CAPI system failures could delay data collection
[5 empty] | 5.8.2. Technical support to survey publicity (MSS will be supporting with logo and uniform design as well as design of promotional materials at the direction of DCM) | 1 | Produce and disseminate promotional materials (posters, banners, digital content) | Ongoing | Insufficient training time leading to field errors
|  |  | MFDB |  | 5.8.3. Technical support to survey trainings (MSS will support in training for the use of tablets and software navigation, and to lead any discussions of a technical nature. MSS would also identify remedial training needs if data quality issues arise.) | 1 | Provide training on tablet use, field procedures, and troubleshooting | Ongoing | Late changes to questionnaires impacting CAPI programming
[5 empty] | 5.8.4. Technical support to survey fieldwork and quality monitoring (MSS to lead in developing the monitoring dashboard) | 1 | Develop and operationalize real-time fieldwork monitoring dashboards | January | Limited partner coordination causing inconsistent survey procedures
[5 empty] | 5.8.5. Technical support to survey data processing, cleaning, and analysis (MSS to work with partners in these efforts towards a clean dataset that can be anonymized for publication in our data archive. MSS to also work with partners on analysis in partnership with responsible officers) | 1 | Assist partners with data processing, cleaning, anonymization, and analysis | Jan - Dec | Delays in data cleaning due to incomplete or poor-quality field data
[5 empty] | 5.8.6. Facilitate survey partnership relations (coordination role with partners when planning a survey). | 1 | Coordinate survey planning and partnership meetings with stakeholders | Ongoing
|  | TOTAL BUDGET |  | 1920000

## 1606-Economics
Strategy Objective | Code | Program | Activity | Budget | Output/Service Target | Target | Action | Due Date | Comments/Risks | Progress
| 6.1 | International Merchandise Trade Statistics (IMTS) | MFDB | 100000 | 6.1.1 Produce IMTS report - 2025 | 1 | Collect, compile and analyse monthly IMTS Data | Jan - Dec | i) Natural Disaster | Complete
[5 empty] | 6.1.2. Produce QSI Monthly Trade tables | 11 |  | Quarterly | ii) Government net work | Up to date
[5 empty] | 6.1.3. Produce National Accounts Trade data set | 1 |  | June | iii) Back up from internal server | In Progress
[5 empty] | 6.1.4 Produce monthly Construction material data | 4 |  | Quartery | iv) Transfer of skills for sustainability | Up to date
[5 empty] | 6.1.5 Additional table on NCD goods | 11 |  | Monthly |  | Up to date
| 6.2 | Internatinal Visitors Arrival Statistics (IVA) | MFDB | 100000 | 6.2.1. Produce monthly IVA Statistics | 15 | Collect, compile and analyse monthly IVA Data | Monthly | i) Natural Disaster | Up to date
[5 empty] | 6.2.2 Improve coverage - Luganville Data | 1 |  | 2025-06-30 | ii) Government net work | Not Yet Started
[5 empty] | 6.2.3 IVA Automate Data Processing in R - RAP | 1 | Automate IVA Data Processing in R | 2025-09-30 | iii) Delay in response from Immigration | In Progress
| 6.3 | Consumer Price Index (CPI) | MFDB | 100000 | 6.3.1. Produce four quarterly CPI reports | 4 | Collect, compile and analyse quarterly CPI | Quarterly | i) Natural Disaster | Up to date
[5 empty] | 6.3.2. Internationla Price Comparasion (ICP) | 3 | Collect prices for comparison with other regions | Quarter 1 | ii) Over-load with Project (HIES) | In Progress
[5 empty] | 6.3.3. Food Price Index | 3 | Draft review of the first report | Quarterly | iii) Over-load and timimg might not be sufficcient | In Progress
[5 empty] | 6.3.4. Auotomate CPI data collection using CAPI | 1 | Map out the process | Quarter 3 | iv) Back up of files on individual drives or USBs | Not Yet Started
[5 empty] | 6.3.4. Develop Monthly CPI road Map | 1 | Map out the process | Quarter 4 |  | Not Yet Started
| 6.4 | Quarterly Statistical Indicator (QSI) | MFDB |  | 6.4.1. Produce 4 quarterly Statistical Indicators | 4 | Collect, Compile and analyse the QSI | Quaterly | i) Natural Disaster | Up to date
[5 empty] | 6.4.2. Produce standard report layout with French translation | 1 | French translaion | Quarterly | ii) Government net work | Not Yet Started
[5 empty] | 6.4.3. Improve the coverage of indicators in QSI, Vehicle registration, Building Permits | 3 | Collection of new indicators | 2025-09-30 | iii) Non-response | Not Yet Started
| 6.5 | National Accounts | MFDB | 500000 | 6.5.1. Produce 2025 GDP Preliminary release | 1 | Collect, compile and analyse annual GDP report | 2025-09-30 | i) Natural Disaster | In Progress
[5 empty] | 6.5.2. Review and Finalize Agricultural Census Report and update baseline indicators in national accounts framework. | 1 | Update Agricculture, forestry and fisheries base line data form Census results. | 2025-09-30 | ii) Government net work | In Progress
[5 empty] | 6.5.3. Develop the Quarterly National Accounts (QNA) road Map | 1 | Develop the QNA framework | Quarter 4 | iii) Missing record, complete data set | Not Yet Started
| 6.6 | Market Survey | MFDB | 50000 | 6.6.1 Produce 4 Quarterly market survey report | 4 | Collect, compile and analyse MS report | Quarterly | i) Natural Disaster | Up to date
[5 empty] | 6.6.2 Review users needs for Market Survey Publication | 1 | Review publication for user needs | 2025-06-30 | ii) Over-load with Project (HIES) | Not Yet Started
[5 empty] | 6.6.3 Coordinate Data anonmaization of 2022 Agriculture census data | 1 | Share Data set with key Stake holder | 2025-06-30 | iii) Avaliable of technical support | Not Yet Started
| 6.7 | Business Registry System (SBR) | MFDB | 50000 | 6.7.1 An active Business registry system (SBR) | 1 | Collect, compile and update BR system | Quarterly | i) Natural Disaster | In Progress
[5 empty] | 6.7.2. Updating the SBR using Business licience, VAT and VFSC registration. | 1 |  | Quarterly | ii) Delay in response from data providers | In Progress
[5 empty] | 6.7.3 Classification of VanSIC/ISIC, IU and Legal states | 1 | Classification of Industies, Institutional units and legal states | Quarterly | iii) Back up of files on individual drives or USBs | In Progress
| 6.8 | Standard Operating Procedure of regular releases | MFDB | 50000 | 6.8.1 Produce SOPs and documentation for regular releases (IAS, IMTS, MS, CPI, QSI, GDP) | 1 | Finalize submit the SOP to signed by CS | 2025-11-30 | i) SOP can be generic and flexible for further revision for time. | In Progress
| 6.9 | Training and Capacity building | MFDB | 50000 | 6.9.1 Conduct 1 in-house R-refresher training | 3 | On the job training | Quarterly | i) Hand on with the existing system - IVA, IMTS, CPI | In Progress
[5 empty] | 6.9.2 GDP Methodological changes and new system development | 2 | Going through the system with the NA team | Quarterly | ii) In-house training on the new National Accounts system | In Progress
| 6.1 | Labour Force Tracker | MFDB |  | 6.10.1 Develop a quarterly labour force publication using administrative data from VNPF | 1 | Data access from key stakeholders | 2025-06-30 | i) Delay in accessing the require administrative records | Not Yet Started
| 6.11 | HIES 2026-2027 support Project Team | MFDB |  | 6.11.1 Training of trainers and interviewers | 1 | Prepare training materials | 2025-02-15 | i) Natural Disaster | Complete
[5 empty] | 6.11.2 Finalize Training Manual | 1 | Prepare the Manual on time | 2025-02-20 | ii) Proper Questionnaire pre-testing | Complete
[5 empty] | 6.11.3 Questionnaire translation | 1 | Coordinate with the translation team | 2025-02-20 | iii) Any delay will affect the over all project duration | Complete
[5 empty] | 6.11.4 Training of Enumerators | 1 | Travelling logistic sort on time | 2025-02-10 |  | Complete
[5 empty] | 6.11.5 Logistical support | 1 | Clear communication | Quarterly |  | In Progress
| 6.12 | Membership to Macro-Economic Committee (MEC) | MFDB |  | 6.12.1 Progress updated in meeting minutes | 4 | Provide all require data on time | Quarterly | Delay in reqular publication/data request | Up to date
| 6.13 | Customer Service (Client request) | MFDB |  | 6.13.1 90% of request completed | Unlimted | Attempt to all data request | Monthly | Delay in responding | In Progress
| TOTAL BUDGET |  |  | 1000000

## 1607-Social
Strategy Objective | Code | Program | Activity | Budget | Output/Service Target | Target | Action | Due Date | Comments/Risks | Progress
| 7.1 | Stakeholder Support and Engagement | MFDB | 30000 | 7.1.1. Collecttion and Production of Labor Statistics Quaterly Reports | 4 | i. Monthly download of labour mobility data from MIDAS | Quarterly | VBoS team to work closely with the labor department on their domestic and overseas employment dataset to produce quarterly reportings | In-Progress
ii.Data Cleaning, processing and analysis
iii.Quaterly review, finalize and publish
iv. Support labor department in developing domestic labor market statistics
|  |  |  | 30000 | 7.1.2. Collection and Production of Infrastructure Statistics | 1 | i. Develop 5 infrastructure indicators | 2026-09-30 | VBoS team will be work with PWD, Civil Aviation, Ports Harbour, etc..on their available datasets | In-Progress
ii. Develop infrastructure data collection plan
iii. Liaise with stakeholders for access to their administrative datasets for data analysis reporting
|  |  |  | 10000 | 7.1.3. Providing support to the DoH and CRIMS with their Death data and compilation of NCD relateed death statistical report - Health Statistics - NCD Report and Annual Report on Deaths | 2 | i. Continuous dialogue with the HIS team within the Department of Health to collaboratively conduct the NCD Steps survey | 2026-06-30 | The challenge would be the availability of the death data, VBoS having access to CRIMS for the extraction of datasets for report compilation | In-Progress
Compile a NCD report (Trades data)
ii. Work with HIS team, CRIMS and SPC to consolidate death data
|  |  |  | 10000 | 7.1.4. Population and Demographic Statistics Registry Draft Plan developed | 1 | i. Draft a work plan | Quarter 2 | Availibility of required dataset from the respective departments such as Civil Registry office and Department of Health | In-Progress
ii. Budget draft plan
iii. Consultation and support CRIMs and other relevant stakeholders
|  |  |  | Donor | 7.1.5. Statistical Training to Provincial Youth Groups | 2 | i. Capacity building of Provincial Youth Groups | Quarter 3 | Funding availibility and members be representative | Completed
|  |  |  | 10000 | 7.1.6. Education Statistics - VANSTA Examination report | 1 | i. Create dashboard using Power BI | Quarter 1 | Allowing access to Education datasets, is it a clean dataset? | In-Progress
ii. Draft policy brief on Literacy and Numeracy
iii. Provide support to review Education digest and statistics report
|  |  |  | 120000 | 7.1.7. Coordinate the National Gender Road Map | 1 | i. Gender National Road Map report: VBoS to liaise with SPC and the DWA on the way forward towards the drafting of the National Gender Road Map | Quarter 1-3 | The Departmentof Women Affairs has to take lead in this initiative and ensure that resources are avaialable for the smooth processes of this roadmap report | In-Progress
[7 empty] | ii. Review Prevalence Domestic Violence Survey (PDVS) findings and assist in launching of PDVS report |  | PDVS Launching done | completed
[5 empty] | 7.1.8 Support with PDVS survey report | 1 | i. Design infographics on PDVS findings |  | dataset to be provided | In-Progress
|  |  |  | Donor | 7.1.9. Task Force Member for the CAT Reporting - United Nation Report | 1 | i. Convention Against Torture Initial Report completed and sent to the UN | Quarter 2 | The Ministry of Justice, Youth and Community Services to ensure that the report reflect the country legal standards and our laws are being reflected in this UN Treaty reporting | Completed
|  |  |  | 20000 | 7.1.10. Court Statistics | 1 | i. Review and Publish court statistics dashboard |  | Dashboard completed and published | Completed
[7 empty] | ii. Request letter to CJ seeking his approval to review court annual report |  | Letter to CJ drafted | In-Progress
|  |  |  | 20000 | 7.1.11. Crime Statistics | 1 | i. Facilitate signing of MOA between VPF and VBoS | Quarter 1-3 | awaiting review and feedback from the Police on the MOA. | Completed
[7 empty] | ii. Draft crime statistical reporting |  | Data be collected from Crime office
|  |  |  | 100000 | 7.1.12. Environment Statistics | 1 | i. Work with the Ocean department to establish preliminary Ocean accounts | Quarter 1 and Quarter 4 | The Ocean affairs rapid response to VBoS on this initiative | In-Progress
ii. Produce preliminary land cover account
| 7.2 | Client Request Support Services | MFDB | 30000 | 7.2.1. Statistical Assistance: Daily advice and queires to clients |  | i. Register client request by individual staff | 2026-12-31 | the availibility of some administrative datasets that is not within reach of the VBoS. | In-Progress
ii. Run request and disseminate
| 7.3 | Statistical Literacy Training | MFDB | 540000 | 7.3.1. Deliver Provincial & Stakeholders Statistical Training | 2 | Develop Pre and Post assessment training form | Quarter 1 | the commitment and the interests of the government stakeholders to learn about the statistics, work commitments | Completed
ii. Develop training material as per assessment outcome
iii. Develop training plan
iv. Logistics arrangements of training (Confirmation of stakeholders list, venue, budget etc)
v. Conduct training
| 7.4 | Population Policy | MFDB | Donor | 7.5.1. VBoS, DSPPAC $ UNFPA identify a local TA | 1 | i. In search of and Identification of a local TA to begin work with the NPP. |  | the availibility of the TA, meeting the UNFPA requirements, the TOR still pending due to checks from UNFPA. | In-Progress
[5 empty] | 7.5.2. Review and signing of the existing TOR by the TA | 1 | ii. the TA must review the TOR before commencing work on the NPP policy
[5 empty] | 7.5.3. Stakeholders Consultation and Awareness | 1 | iii. A wide consultation to be done for various stakeholders
[5 empty] | 7.5.4. TA to begin drafting of NPP | 1 | iv. the TA must begin drafting the NPP with the assistance from VBoS, DSPPAC and UNFPA team.
[5 empty] | 7.5.5. COM Paper submission | 1 | v. the final NPP report must be submitted to the parliament for COM approval on the Policy.
[5 empty] | 7.5.6. NPP Launching and Dissemination | 1 | vi. Review and finalize Policy for launching
PROJECTS
| 7.6 | Disaster Innovative Project | MFDB | Donor | 7.6.1. Finalization of the Disaster MIS System - Capacity Building with Users | 2 | MIS System Capacity Building with National & Provincial Users | Quarter 2 | Awaiting NDMO confirmation on the funding | Completed
| 7.7 | Household Income and Expenditure Survey (HIES) | MFDB | Donor | 7.7.1. Questionnaire translation and Manual review | 1 | i. Input in Labour, Population, Health, Education and Environment related sector | 12 months | Funding availibility and Natural Disaster | Completed
[5 empty] | 7.7.2. 1 application system developed, and 57 interviewers recruited | 1 | ii. Develop Kobo form for applicants, Review applications and selection of 57 interviewer
| 7.9 | Social & Environment Technical Committee | MFDB | 80000 | 7.9.1. Set up 2 Technical Committee | 2 | i. Design TOR of committee members | Quarter 1-2 | availibility of the stakeholders to attend meetings | completed
ii. Letters of appointment
iii. Meeting dates finalized and carried out accordingly
| TOTAL BUDGET |  |  | 1000000

## 1608-Torba
Strategy Objective | Code | Program | Activity | Budget | Output/Service Target | Target | Action | Due Date | Comments/Risks | Progress
DEVELOP A HARMONIZED NATIONAL STATISTICS OFFICE | 8.1 | 10 year Data Collection Plan | MFDB | Donor | HIES
[5 empty] | 8.1.1. Recruitment | 1 | Assist Port Vila Team | 2026 | Natural Disaster and Pandemic
[5 empty] | 8.1.2. Logistics | 1 | Assist Port Vila Team
[5 empty] | 8.1.3. Training of Enumerators | 1 | Assist Port Vila Team |  | Mitigation: Liaise with Project Coordinator for way forward
[5 empty] | 8.1.4. Publication | 1 | Assist Port Vila Team
[5 empty] | 8.1.5. 12 Months Field Work Collection | 1 | Field work collection monitoring in Torba
| 8.2 | Production of Regular Publications | MFDB |  | PSI
|  |  |  | 200000 | 8.2.1. Torba Provincial Statistical Indicator | 1 | Complete Torba PSI 2023-2024 | 31.12.26 | Natural Disaster and Pandemic
|  |  |  | 25000 | 8.2.2. Torba Provincial Business License Registry Updates | 1 | Annual Business License Registry updates | 31.12.26 | Mitigation: Seek Assistance to ensure PSI and Registry are updated
| 8.3 | Administration and Planning | MFDB | 100000 | 8.3.1. DCM Torba Workplan Monitored | 1 | Coordinate and Facilitate Plans | 31.12.26 | Delay in Plans due to Natural Disaster or unforseen activities.
[5 empty] | 8.3.2. Torba Monthly Reporting on DCM Activities | 12 | Coordinate Activities and compile a report | 31.12.26
[5 empty] | 8.3.3. Torba Quaterly Reporting on DCM Activities | 4 | Coordinate Activities and compile a report | 31.12.26 | Mitigation: Push Activites to a later date and notify superiors of the changes
|  |  |  | 300000 | 8.3.4. Capacity Building for Torba Officer | 1 | Liaise with Admin for Training Opportunity | 31.12.26
|  |  |  | 25000 | 8.3.5. Torba Inventory System Updated | 1 | Update Inventory System | 31.12.26
|  |  |  | 200000 | 8.3.6. Effective Management of Torba Operation | 1 | Liaise with Admin to ensure effectiveness of Admin support | 31.12.26
|  |  |  | 500000 | 8.3.7. Torba Provincial Event | 1 | Provide assistance and coordination during provincial events in Torba (North). | 31.12.26
|  |  |  | 100000 | 8.3.8. Torba Fleet Management Reporting | 4 | Official Use of Truck and Boat | 31.12.26
| 8.4 | Other Activities | MFDB | 50000 | 8.4.1. Torba VBoS Representative in PTAC | 12 | Present during every PTAC Meeting | 31.12.26
|  |  |  | 50000 | 8.4.2. Develop strong relationship with stakeholders and all enquiries are dealth with in a timely manner | 1 | Facilitate all enquiries received from stakeholders | 31.12.26
|  |  |  | 50000 | 8.4.3. Provide technical support for a smooth running process of the survey | 1 | Provide assistance and coordination | 31.12.26
|  | TOTAL BUDGET |  | 1600000

## 1609-Sanma
Strategy Objective | Code | Program | Activity | Budget | Output/Service Target | Target | Action | Due Date | Comments/Risks | Progress
DEVELOP A HARMONIZED NATIONAL STATISTICS OFFICE | 9.1 | 10 year Data Collection Plan | MFDB | Donor | HIES
[5 empty] | 9.1.1. Recruitment | 1 | Assist Port Vila Team | 2026 | Natural Disaster and Pandemic
[5 empty] | 9.1.2. Logistics | 1 | Assist Port Vila Team
[5 empty] | 9.1.3. Training of Enumerators | 1 | Assist Port Vila Team |  | Mitigation: Liaise with Project Coordinator for way forward
[5 empty] | 9.1.4. Publication | 1 | Assist Port Vila Team
[5 empty] | 9.1.5. 12 Months Field Work Collection | 1 | Field work collection monitoring in Sanma
| 9.2 | Production of Regular Publications | MFDB |  | CPI
|  |  |  | 20000 | 9.2.1. 26 Data Collection and Entries | 26 | Luganville CPI Data Collection & Entry Forthnight | 31.12.26
|  |  |  | 20000 | 9.2.2. 4 Data Collection and Entries | 4 | Luganville CPI Data Collection and Entry Quarterly | 31.12.26
Market Survey
|  |  |  | 20000 | 9.2.3. 26 Data Collection and Entries | 26 | Luganville Market Survey (MS2) Data Collection | 31.12.26
PSI
|  |  |  | 200000 | 9.2.4. Sanma Provincial Statistical Indicator | 1 | Facilitate the process to get all data | 31.12.26 | Natural Disaster and Pandemic
[5 empty] | QSI |  |  |  | Mitigation: Registry are updated
|  |  |  | 20000 | 9.2.5. Quarterly Statistical Indicator | 1 | Assist Economic Unit data collection and stakeholder relationship | 31.12.26
|  |  |  | 20000 | 9.2.6. Business Registration | 1 | Annual Business License Registry updates | 31.12.26
| 9.3 | Administration and Planning | MFDB | 100000 | 9.3.1. DCM Santo Workplan Monitored | 1 | Coordinate and Facilitate Plans | 31.12.26 | Delay in Plans due to Natural Disaster or unforseen activities.
[5 empty] | 9.3.2. Santo Monthly Reporting on DCM Activities | 12 | Coordinate Activities and compile a report | 31.12.26
[5 empty] | 9.3.3. Santo Quaterly Reporting on DCM Activities | 4 | Coordinate Activities and compile a report | 31.12.26 | Mitigation: Push Activites to a later date and notify superiors of the changes
|  |  |  | 300000 | 9.3.4. Capacity Building for Santo Officers | 1 | Liaise with Admin for Training Opportunity | 31.12.26
|  |  |  | 10000 | 9.3.5. Sanma Inventory System Updated | 1 | Update Inventory System | 31.12.26
|  |  |  | 2000000 | 9.3.6. Effective Management of Sanma Operation | 1 | Liaise with Admin to ensure effectiveness of Admin support | 31.12.26
|  |  |  | 500000 | 9.3.7. Sanma Provincial Event | 1 | Provide assistance and coordination during provincial events in Sanma (North). | 31.12.26
|  |  |  | 300000 | 9.3.8.Sanma Fleet Management Reporting | 4 | Official Use of Truck and Boat | 31.12.26
| 9.4 | Other Activities | MFDB | 40000 | 9.4.1. Sanma VBoS Representative in PTAC | 12 | Present during every PTAC Meeting | 31.12.26
|  |  |  | 50000 | 9.4.2. Develop strong relationship with stakeholders and all enquiries are dealth with in a timely manner | 1 | Facilitate all enquiries received from stakeholders | 31.12.26
|  |  |  | 50000 | 9.4.3. Ad-hoc Survey | 1 | Provide techinical assistance and support for a smooth running process of the survey. | 31.12.26
|  | TOTAL BUDGET |  | 3650000

## 1610-Malampa
Strategy Objective | Code | Program | Activity | Budget | Output/Service Target | Target | Action | Due Date | Comments/Risks | Progress
DEVELOP A HARMONIZED NATIONAL STATISTICS OFFICE | 10.1 | 10 year Data Collection Plan | MFDB | Donor | HIES
[5 empty] | 10.1.1. Recruitment | 1 | Communicate with publicity team in Vila | 2026 | Natural Disaster and Pandemic
[5 empty] | 10.1.2. Logistics | 1 | Communicate with recruitment team in Vila
[5 empty] | 10.1.3. Training of Enumerators | 1 | Get Transport cost from all area councils |  | Mitigation: Liaise with Project Coordinator for way forward
[5 empty] | 10.1.4. Publication | 1 | Assist Port Vila Team
[5 empty] | 10.1.5. 12 Months Field Work Collection | 1 | Field work collection monitoring in Malampa
| 10.2 | Production of Regular Publications | MFDB |  | PSI
|  |  |  | 300000 | 10.2.1. Malampa Provincial Statistical Indicator | 1 | Send follow up emails and phone calls | 31.12.26 | Natural Disaster and Pandemic
[5 empty] | 10.2.2. Malampa Provincial Business License Registry Updates | 1 | Annual Business License Registry updates | 31.12.26 | Mitigation: Seek Assistance to ensure PSI and Registry are updated
| 10.3 | Administration and Planning | MFDB |  | 10.3.1. DCM Malampa Workplan Monitored | 1 | Coordinate and Facilitate Plans | 31.12.26 | Delay in Plans due to Natural Disaster or unforseen activities.
|  |  |  | 50000 | 10.3.2. Malampa Monthly Reporting on DCM Activities | 12 | Coordinate Activities and compile a report | 31.12.26
[5 empty] | 10.3.3. Malampa Quaterly Reporting on DCM Activities | 4 | Coordinate Activities and compile a report | 31.12.26 | Mitigation: Push Activites to a later date and notify superiors of the changes
[5 empty] | 10.3.4. Capacity Building for Malampa Officer | 1 | Liaise with Admin for Training Opportunity | 31.12.26
[5 empty] | 10.3.5. Malampa Inventory System Updated | 1 | Update Inventory System | 31.12.26
|  |  |  | 930000 | 10.3.6. Effective Management of Malampa Operation | 1 | Liaise with Admin to ensure effectiveness of Admin support | 31.12.26
|  |  |  | 280000 | 10.3.7. Malampa Provincial Event | 1 | Provide assistance and coordination during provincial events in Malampa (North). | 31.12.26
|  |  |  | 30000 | 10.3.8. Coordinate Surveys and Censuses at the Provincial Level | 4 | Good communication and planning with survey and census leads to ge high qualiy data collection. | 31.12.26
| 10.4 | Other Activities | MFDB | 100000 | 10.4.1. Malampa VBoS Representative in PTAC | 12 | Present during every PTAC Meeting | 31.12.26
|  |  |  | 50000 | 10.4.2. Develop strong relationship with stakeholders and all enquiries are dealth with in a timely manner | 1 | Facilitate all enquiries received from stakeholders | 31.12.26
|  |  |  | 50000 | 10.4.3. Provide technical support for a smooth running process of the survey | 1 | Provide assistance and coordination | 31.12.26
|  | TOTAL BUDGET |  | 1790000

## 1611-Penama
Strategy Objective | Code | Program | Activity | Budget | Output/Service Target | Target | Action | Due Date | Comments/Risks | Progress
DEVELOP A HARMONIZED NATIONAL STATISTICS OFFICE | 11.1 | 10 year Data Collection Plan | MFDB | Donor | HIES
[5 empty] | 11.1.1. Recruitment | 1 | Assist Port Vila Team | 2026 | Natural Disaster and Pandemic
[5 empty] | 11.1.2. Logistics | 1 | Assist Port Vila Team
[5 empty] | 11.1.3. Training of Enumerators | 1 | Assist Port Vila Team |  | Mitigation: Liaise with Project Coordinator for way forward
[5 empty] | 11.1.4. Publication | 1 | Assist Port Vila Team
[5 empty] | 11.1.5. 12 Months Field Work Collection | 1 | Field work collection monitoring in Penama
| 11.2 | Production of Regular Publications | MFDB |  | PSI
|  |  |  | 200000 | 11.2.1. Penama Provincial Statistical Indicator | 1 | Complete Penama PSI | 31.12.26 | Natural Disaster and Pandemic
[5 empty] | 11.2.2. Penama Provincial Business License Registry Updates | 1 | Annual Business License Registry updates | 31.12.26 | Mitigation: Seek Assistance to ensure PSI and Registry are updated
| 11.3 | Administration and Planning | MFDB |  | 11.3.1. Quarterly Report to DCM and Admin Manager | 4 | Coordinate and Facilitate Plans and comiple report | 31.12.26 | Delay in Plans due to Natural Disaster or unforseen activities.
[5 empty] | 11.3.4. Capacity Building for Penama Officer | 1 | Liaise with Admin for Training Opportunity | 31.12.26
[5 empty] | 11.3.5. Penama Inventory System Updated | 1 | Update Inventory System | 31.12.26 | Mitigation: Push Activites to a later date and notify superiors of the changes
|  |  |  | 800000 | 11.3.6. Effective Management of Penama Operation | 1 | Liaise with Admin to ensure effectiveness of Admin support | 31.12.26
[5 empty] | 11.3.7. Penama Provincial Event | 1 | Provide assistance and coordination during provincial events in Penama. | 31.12.26
[5 empty] | 11.3.8. Penama Fleet Management Reporting - Quad | 4 | Status of the VBoS Quad for Penama | 31.12.26
| 11.4 | Other Activities | MFDB |  | 11.4.1. Penama VBoS Representative in PTAC | 12 | Present during every PTAC Meeting | 31.12.26
[5 empty] | 11.4.2. Develop strong relationship with stakeholders and all enquiries are dealth with in a timely manner | 1 | Facilitate all enquiries received from stakeholders | 31.12.26
[5 empty] | 11.4.3. Provide technical support for a smooth running process of the survey | 1 | Provide assistance and coordination | 31.12.26
|  | TOTAL BUDGET |  | 1000000

## 1612-Tafea
Strategy Objective | Code | Program | Activity | Budget | Output/Service Target | Target | Action | Due Date | Comments/Risks | Progress
DEVELOP A HARMONIZED NATIONAL STATISTICS OFFICE | 12.1 | 10 year Data Collection Plan | MFDB | Donor | HIES
[5 empty] | 12.1.1. Recruitment | 1 | Assist Port Vila Team | 2026 | Natural Disaster and Pandemic
[5 empty] | 12.1.2. Logistics | 1 | Assist Port Vila Team
[5 empty] | 12.1.3. Training of Enumerators | 1 | Assist Port Vila Team |  | Mitigation: Liaise with Project Coordinator for way forward
[5 empty] | 12.1.4. Publication | 1 | Assist Port Vila Team
[5 empty] | 12.1.5. 12 Months Field Work Collection | 1 | Field work collection monitoring in Tafea
| 12.2 | Production of Regular Publications | MFDB |  | CPI
|  |  |  | 20000 | 12.2.1. 26 Data Collection and Entries | 26 | Lenakel CPI Data Collection & Entry Forthnight | 31.12.26
|  |  |  | 20000 | 12.2.2. 4 Data Collection and Entries | 4 | Lenakel CPI Data Collection and Entry Quarterly | 31.12.26 | Natural Disaster and Pandemic
[5 empty] | Market Survey |  |  |  | Mitigation: Registry are updated
|  |  |  | 20000 | 12.2.3. 26 Data Collection and Entries | 26 | Lenakel Market Survey Data Collection | 31.12.26
[5 empty] | 12.2.4. Business Registry | 1 | Assist in Tafea Busness Data Collection | 31.12.26
PSI
|  |  |  | 200000 | 12.2.5. Tafea Provincial Statistical Indicator | 1 | Complete 2023-2025 PSI | 31.12.26
| 12.3 | Administration and Planning | MFDB | 100000 | 12.3.1. Quarterly Reporting to DCM and Admin Manager | 4 | Coordinate and Facilitate Plans | 31.12.26 | Delay in Plans due to Natural Disaster or unforseen activities.
[5 empty] | 12.3.2. Hire an Intern to assist with Tafea Operations | 1 | Liaise with Admin to facilitate | 30.01.26
|  |  |  | 300000 | 12.3.4. Capacity Building for Tafea Officer | 1 | Liaise with Admin for Training Opportunity | 31.12.26 | Mitigation: Push Activites to a later date and notify superiors of the changes
|  |  |  | 10000 | 12.3.5. Tafea Inventory System Updated | 1 | Update Inventory System | 31.12.26
|  |  |  | 2000000 | 12.3.6. Effective Management of Tafea Operation | 1 | Liaise with Admin to ensure effectiveness of Admin support | 31.12.26
[5 empty] | 12.3.7. Statistical Literacy | 1 | Report to Manager DCM | 31.07.26
|  |  |  | 500000 | 12.3.8. Tafea Provincial Event | 1 | Provide assistance and coordination during provincial events in Tafea. | 31.12.26
[5 empty] | 12.3.9. New Photocopy Machine | 1 | Liaise with Finance for approval and payment | 30.03.26
|  |  |  | 300000 | 12.3.10. Tafea Fleet Management - New Vehicle | 1 | Liaise with Admin and CS for approval | 31.12.26
| 12.4 | Other Activities | MFDB | 40000 | 12.4.1. Tafea VBoS Representative in PTAC | 12 | Present during every PTAC Meeting | 31.12.26
|  |  |  | 50000 | 12.4.2. Develop strong relationship with stakeholders and all enquiries are dealth with in a timely manner | 1 | Facilitate all enquiries received from stakeholders | 31.12.26
|  |  |  | 50000 | 12.4.3. Ad-hoc Survey | 1 | Provide techinical assistance and support for a smooth running process of the survey. | 31.12.26
|  | TOTAL BUDGET |  | 3610000